| Fly or Die: Production Schedule |  |
| --- | --- |
| Date/Time: | Details: |  |
| Tuesday, April 9th |  |  |
| 9:00am to 1:00pm | Tent load in and set up on-site |  |
| 9:00am to 1:00pm | Staging, lighting, audio, video set-up by Stray Production |  |
| 1:00pm to 1:45pm | Crew lunch break |  |
| 2:00pm to 5:00pm | Test audio, lighting and video equipment |  |
|  | Simultaneous set-up (inside and outside) |  |
| Wednesday, April 10th |  |  |
| 8am to 6:00pm | Tech and set-up by Atomic Design |  |
| 9:00am to 12:00pm | Sticking QR codes on wooden dragons (by HBO Max Team members) |  |
| 1:00pm to 2:00pm | Crew lunch break |  |
| 4:00pm to 7:00pm | Atomic tests equipment, effects, and other provided production elements |  |
| Thursday, April 11th |  |  |
| 7:00am to 8:00am | Talent (actors and host) arrival and check-in |  |
| 8:00am to 9:00am | Max Team arrival and check-in |  |
| 8:30am to 12:00pm | Talent rehearsal |  |
| 9:30am to 10:30am | Max Team assigned duties for event |  |
| 10:45am to 1:00pm | Max Team runs through interactive events and rehearses duties for event |  |
| 12:00pm to 1:00pm | Talent lunch break |  |
| 1:00pm to 2:00pm | Max Team lunch break |  |
| 1:15pm to 1:30pm | Talent assigned sections to work in |  |
| 1:45pm to 3:00pm | Just actors costume fittings |  |
| 2:15pm to 3:00pm | Max Team and food/drink service meeting – discuss plans for day of event |  |
| 3:15pm to 4:45pm | Actors’ rehearsal with set, production elements and props |  |
| 3:15pm to 4:45pm | Host rehearsal on stage |  |
| 5:00pm to 7:00pm | Actors, Host, and Max Team rehearse together |  |
|  | Simultaneous rehearsals |  |
| Friday, April 12th |  |  |
| 7:00am to 1:00pm | Tech rehearsal (equipment and production elements) by Atomic Design |  |
| 9:00am to 10:00am | Chairs, tables, and linens delivery |  |
| 9:00am to 9:30am | Talent arrival |  |
| 9:45am to 11:45pm | Talent costume and makeup for dress rehearsal |  |
| 10:30am to 1:00pm | Chairs, tables, and linen set up by Max Team |  |
| 10:30am to 1:00pm | Videographer for single-camera stream arrival and set-up, test equipment |  |
| 12:00pm to 1:00pm | Talent and Max Team meeting |  |
| 1:00pm to 2:00pm | Crew lunch break |  |
| 2:15pm to 7:00pm | Full dress rehearsal (actors, tech, max team, and host) |  |
| Saturday, April 13th |  |  |
| 6:00am | Max team and security arrival |  |
| 6:15am to 7:00am | Max Team meeting/check-in |  |
| 7:00am | Talent arrival |  |
| 7:30am to 9:00am | Talent gets into costume and makeup |  |
| 7:30am to 9:00am | Merch arrival and set-up on tables |  |
| 9:30am to 11:30pm | Food and drink services arrive and set up |  |
| 9:30am to 11:00am | Quick rehearsal/walk through with Actors, Host and Max Team |  |
| 10:00am to 11:30am | Videographer for single-camera stream arrival and final equipment testing |  |
| 11:00am to 11:45am | Everyone into positions and activate necessary production elements |  |
| 12:00pm | Event start and guest arrivals |  |
| 12:00pm to 4:45pm | Interactive event experiences for guests |  |
| 1:00pm to 3:00pm | Revolving crew lunch breaks |  |
| 2:00pm | Fourth Wing author and actors' arrival |  |
| 2:30pm to 4:00pm | Fourth Wing author and actors wait in green room, get makeup touch ups if necessary, and director runs them through event |  |
| 4:00pm to 4:45pm | Announced incremental warnings for guests for start of Q&A |  |
| 5:00pm | Q&A start time |  |
| 6:30pm to 6:45pm | Q&A end time |  |
| 7:00pm to 7:15pm | End of event/guests escorted out |  |
| 7:00pm | Fourth Wing authors and actors exit |  |
| 7:15pm to 8:15pm | Crew dinner |  |
| 7:30pm | Talent, videographer, security dismissed |  |
| 8:30pm to 11:00pm | Initial breakdown starts (tables, chairs, merch, linens, food, rented equipment packed) |  |
| Sunday, April 14th |  |  |
| 9:00am to 10:00am | Chairs, tables, and linens picked up |  |
| 9:00am to 12:00pm | Atomic production elements strike |  |
| 12:00pm to 2:00pm | Tent strike and return |  |
| 2:00pm to 3:00pm | Crew lunch |  |
| 3:00pm to 4:00pm | Rented equipment loaded into Max Team trucks, to be returned after they leave site |  |